| Weekly Project SCRUM Report |
| --- |
| Date: Mar 16th, 2023 |
| Project Name: Gun Violence - SP23 |
| Team Members: Sai Surya Varshith, Hitanshi Jain, Peiying Ye, Yuhe Bian |
| Tasks Completed This Week:   * Organize previous deliverable to prepare checkpoint 1 for client meeting presentation – Everyone * Refining previous analysis on Question 2 with more detailed explanation – Peiying * Pre-process for the extension data set—Yuhe * Finish extension proposal template —Yuhe * Worked on comparing gun violence in D4 and rest of the Boston city - Surya * Worked on comparing all the crime incidents in D4 and the Boston city - Hitanshi * Worked on visualizing year wise violences in Crime incidents data - Surya and Hitanshi |
| Plans for Next Week:   * Work on analysis for the rest of the questions – Everyone * Work on presentation outline – Everyone * Focus on the matching district part in the presentation – Peiying * Figure out more dataset to perform analysis – Peiying * Collection and analysis for the extension data sets—Yuhe * Investigate the primary shooting hubs in D4 and determine if they are happening at public places or not. - Surya * Analyze the role of school students or age groups in incidents of gun violence. - Hitanshi |
| Obstacles and Questions:   * Have a more detailed deliverable for the future, with more explanation on our analysis |
| Met with the client recently? When is the next meeting with the client?:   * Last Meeting was on March 3rd, next meeting will be on March 24th |